## TestScenarios
SNO | Scenario | No.of Test Cases
1 | An user application can login into his account. | 5
2 | A customer can see his account statements. | 1
3 | A customer can have multiple bank accounts. | 1
4 | A customer can view balance of his accounts only. | 1
5 | A customer can transfer funds from his own account to any destination account. | 1
6 | A customer can change password of his account only. | 1
7 | A customer can see customized statements of his accounts only. | 1

## TestCases
TC #ID | User Story ID | Feature / Title | User Story | Steps | Test Data | Expected result | Actual result | Status | Comments
TC_BANK_001 | US001 | [6 empty] | PASSED
TC_BANK_002 | US001 | [6 empty] | PASSED
TC_BANK_003 | US001 | [6 empty] | PASSED
TC_BANK_004 | US001 | [6 empty] | PASSED
TC_BANK_005 | US001 | [6 empty] | PASSED
TC_BANK_006 | US002 | [6 empty] | PARTIAL PASSED
TC_BANK_007 | US003 | [6 empty] | PARTIAL PASSED
TC_BANK_008 | US004 | [6 empty] | PASSED
TC_BANK_009 | US005 | [6 empty] | FAILED(P2)
TC_BANK_010 | US006 |  |  |  | N/A |  |  | FAILED(P1)
TC_BANK_011 | US007 |  |  |  | N/A |  |  | PARTIAL PASSED
An user application can login into his account.
As a user of this application, I want to be able to sign in into my account so that I can check and manage it.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
UserID: 1303
Password: Guru99
Login process successfully done.
As expected
An user application can login into his account.
As a user of this application, I want to be able to sign in into my account so that I can check and manage it.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and invalid password.
3) Click on "Login" button.
UserID: 1303
Password: Guru98
Login process has failed.
As expected.
An user application can login into his account
As a user of this application, I want to be able to sign in into my account so that I can check and manage it.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter invalid UserID and valid password.
3) Click on "Login" button.
UserID: 1304
Password: Guru99
Login process has failed.
As expected.
An user application can login into his account.
As a user of this application, I want to be able to sign in into my account so that I can check and manage it.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter invalid UserID and invalid password.
3) Click on "Login" button.
UserID: 1304
Password: Guru98
Login process has failed.
As expected.
An user application can login into his account.
As a user of this application, I want to be able to sign in into my account so that I can check and manage it.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Leave the UserID and Password fields blank.
3) Click on "Login" button.
N/A
Login process has failed.
As expected.
A customer can see his accounts statements.
As a customer I want to be able to see my accounts statements so that I can I can manage them
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access "Mini Statement" field
5) Select account number from dropdown list
6) Click on "Submit" button
N/A
The customer is able to see his accounts statements.
There is no option to introduce an unexcepted account in the special fields.
So the system cannot throw any errors if needed.
A customer can have multiple bank accounts.
As a customer I want to be able to have multiple accounts so that I can split my actions and income.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access "Mini Statement" field
5)From "Mini Statement Form" access "Account Number" drop down list
6)Select the desired account
N/A
The customer is able to have multiple bank accounts.
The customer is able to access only his accounts that are registered in the system data base.
He cannot create new accounts.
A customer can view balance of his accounts only.
As a customer I want to be able to view the balance of my accounts so that I can analyze my cash flows.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access the "Balance Enquiry" field
5) Select account number from the database
6) Click on "Submit" button
7) Vizualise the account balance
N/A
The customer is able to verify his only his accounts balances.
As expected.
A customer can transfer funds from his own account to any destination account.
As a customer i want to be able to transfer funds from my accounts to any other account so that I can get the full control of my bank accounts.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access the "Mini Statement" field
5)Select account number from database
6) Click on "Submit"
7) Vizualise the last five transactions details for the selected account.
N/A
The customer is able to proceed transfers from his accounts to any destination.
The application does not offer the posibility to select custom transfer funds destinations.
Only the preseted one are registered and can available for check.
A customer can change password of his account only.
As a customer a want to be able to change my account password so that I can control my account and increase its security if needed.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) N/A
The customer is able to change his account password.
A customer can see customized statements of his accounts only.
As a customer I want to be able to see my account details so that I can properly take action.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access "Mini Statement" field
The customer is able to see his accounts statements.
This functions was not implemented even in the latest release of the app.
Just a few items from the client's list are available to see for customer accounts.
The rest of them does not exist.
Development team should review this functionality if it's on client requirements list.
"New account" feature should be implemented xo that the customer is able to own multiple accounts.
The option to add customized transaction destination needed to be implemented.
This functionality is crucial for customers accounts privacy and security.
It's in the top list of detected defects.
The backog should be consulted once again and missing items should be added in user interface.

## BugReport
QUALITY ASSURANCE | [10 empty] | DEVELOP
Bug ID | Module Name | Build no | Description | TC#ID | Steps to replicate bug | Screenshot | Severity | Priority | Reported by | Assigned to | Resolution | Status | Fixed Date
BANK_001 | Bank management | 2 |  | TC_BANK_006 |  |  | S3 | P3 | Filip Neagoe | Harry | Accepted | In progress | Unknown
BANK_002 | Bank management | 2 |  | TC_BANK_007 |  |  | S3 | P3 | Filip Neagoe | Nick | Accepted | Open | Unknown
BANK_003 | Bank management | 2 |  | TC_BANK_009 |  |  | S2 | P2 | Filip Neagoe | Nick | Accepted | Open | Unknown
BANK_004 | Bank management | 2 |  |  |  |  | S1 | P1 | Filip Neagoe | Harry | Accepted | Open | Unknown
BANK_005 | Bank management | 2 |  |  |  |  | S3 | P3 | Filip Neagoe | Nick | Accepted | Open | Unknown
There is no option to introduce an unexcepted account in the special fields.
So the system cannot throw any errors if needed
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access "Mini Statement" field
5) Select account number from dropdown list
6) Click on "Submit" button
A customer can have multiple bank accounts.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access "Mini Statement" field
5)From "Mini Statement Form" access "Account Number" drop down list
6)Select the desired account
A customer can transfer funds from his own account to any destination account.
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access the "Mini Statement" field
5)Select account number from database
6) Click on "Submit"
7) Vizualise the last five transactions details for the selected account
A customer can change password of his account only.
TC_BANK_010
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) N/A
A customer can see customized statements of his accounts only
TC_BANK_011
1) Access
"http://demo.guru99.com/Agile_Project/Agi_V1/index.php".
2)Enter valid UserID and valid password.
3) Click on "Login" button.
4) Access "Mini Statement" field

## Agile_ProductBacklog
Project | Bank Account application
Customer | Capital One American Bank
Product Owner | Jim
Scrum Master | Conal
Software development team | Harry (leader), Nick
QA team leader | Filip Neagoe
Epic |  | User Story ID | Feature Title | User Story | Status | Technical Requirements | Acceptance Criteria
|  | US001 | An application user can login into the account. |  | New |  | User is able to login into his account.
|  | US002 | A customer can see his accounts statements. |  | New
|  | US003 | A customer can have multiple bank accounts. |  | New
|  | US004 | A customer can view balance of his accounts only. |  | New
|  | US005 |  |  | New
|  | US006 |  |  | New
|  | US007 |  |  | New
A bank appplication user is able to login into his account.
Epic ID: BankAccount_Epic001
As a user of this application, I want to be able to sign in into my account so that I can check and manage it.
User ID must not be blank. Password must not be blank.
A customer can view, manage and modify only his own accounts.
Epic ID: BankAccount_Epic002
As a customer I want to be able to see my accounts statements so that I can I can manage them.
1. Account number must not be blank. 2. Special character are not allowed. 3. Characters are not allowed.
1. If account no is invalid, system displays an error.
2. If account associate with customer itself, system displays an error.
As a customer I want to be able to have multiple accounts so that I can split my actions and income.
1. Account number must not be blank. 2. Special character are not allowed. 3. Characters are not allowed.
Account number entered should exist in database.
As a customer I want to be able to view the balance of my accounts so that I can analyze my cash flows.
1. Account number must not be blank. 2. Special character are not allowed. 3. Characters are not allowed.
Customer can view balance of only his accounts.
A customer can have transfer funds from his own account to any destination account.
As a customer i want to be able to transfer funds from my accounts to any other account so that I can get the full control of my bank accounts.
Payers account number must not be blank. Special characters are not allowed. Characters are not allowed. Payees account number must not be blank Special characters are not allowed. Characters are not allowed. Amount field must not be blank. Characters are not allowed. Special characters are not allowed. Description cannot be blank.
If the destination account number is not valid, system displays an error "Account ### does not exist!" If these source and destination account numbers are same, system displays an error. If the source account does not have the necessary balance, system displays an error. If the source account is not associate with customer itself, System displays an error.
A customer can change password of only his account.
As a customer a want to be able to change my account password so that I can control my account and increase its security if needed.
Old password must not be blank. New password must not be blank. Enter at least one numeric value. Enter at least one special character. Choose a difficult password. Confirm password must not be blank. Passwords do not match.
If old password is invalid, system displays an error.
A customer can see customized statements of only his own accounts.
As a customer I want to be able to see my account details so that I can properly take action.
Account No - Account Number must not be blank. Account No - Characters are not allowed. Account No - Special characters are not allowed. Minimum transaction value - Special character are not allowed. Minimum transaction value - Amount lower limit is required. Minimum transaction value - Characters are not allowed. Number of transaction - Special character are not allowed. Number of transaction - Minimum transaction value must not be blank. Number of transaction - Character are not allowed.
If account number is invalid, system displays an error. If "From Date" is greater than "To Date" , system displays an error.

## Agile_SprintPlanning
Project | Bank Account application
Customer | Capital One american bank
Product Owner | Jim
Scrum Master | Conal
Software development team | Harry (leader), Nick
QA team leader | Filip Neagoe
Epic |  | User Story ID | Feature Title | User Story | Status | Technical Requirements | Acceptance Criteria | Story Points | Sprint
|  | US001 | An application user can login into the account. |  | New |  | User is able to login into his account. | 4 | 1
|  | US002 | A customer can see his accounts statements. |  | New |  |  | 3 | 1
|  | US003 | A customer can have multiple bank accounts. |  | New |  |  | 2 | 3
|  | US004 | A customer can view balance of his accounts only. |  | New |  |  | 4 | 2
|  | US005 |  |  | New |  |  | 3 | 2
|  | US006 |  |  | New |  |  | 4 | 3
|  | US007 |  |  | New |  |  | 3 | 3
A bank appplication user is able to login into his account.
Epic ID: BankAccount_Epic001
As a user of this application, I want to be able to sign in into my account so that I can check and manage it.
User ID must not be blank. Password must not be blank.
A customer can view, manage and modify only his own accounts.
Epic ID: BankAccount_Epic002
As a customer I want to be able to see my accounts statements so that I can I can manage them.
1. Account number must not be blank. 2. Special character are not allowed. 3. Characters are not allowed.
1. If account no is invalid, system displays an error.
2. If account associate with customer itself, system displays an error.
As a customer I want to be able to have multiple accounts so that I can split my actions and income.
1. Account number must not be blank. 2. Special character are not allowed. 3. Characters are not allowed.
Account number entered should exist in database.
As a customer I want to be able to view the balance of my accounts so that I can analyze my cash flows.
1. Account number must not be blank. 2. Special character are not allowed. 3. Characters are not allowed.
Customer can view balance of only his accounts.
A customer can have transfer funds from his own account to any destination account.
As a customer i want to be able to transfer funds from my accounts to any other account so that I can get the full control of my bank accounts.
Payers account number must not be blank. Special characters are not allowed. Characters are not allowed. Payees account number must not be blank Special characters are not allowed. Characters are not allowed. Amount field must not be blank. Characters are not allowed. Special characters are not allowed. Description cannot be blank.
If the destination account number is not valid, system displays an error "Account ### does not exist!" If these source and destination account numbers are same, system displays an error. If the source account does not have the necessary balance, system displays an error. If the source account is not associate with customer itself, System displays an error.
A customer can change password of only his account.
As a customer a want to be able to change my account password so that I can control my account and increase its security if needed.
Old password must not be blank. New password must not be blank. Enter at least one numeric value. Enter at least one special character. Choose a difficult password. Confirm password must not be blank. Passwords do not match.
If old password is invalid, system displays an error.
A customer can see customized statements of his accounts only.
As a customer I want to be able to see my account details so that I can properly take action.
Account No - Account Number must not be blank. Account No - Characters are not allowed. Account No - Special characters are not allowed. Minimum transaction value - Special character are not allowed. Minimum transaction value - Amount lower limit is required. Minimum transaction value - Characters are not allowed. Number of transaction - Special character are not allowed. Number of transaction - Minimum transaction value must not be blank. Number of transaction - Character are not allowed.
If account number is invalid, system displays an error. If "From Date" is greater than "To Date" , system displays an error.

## TestMetrics
Test Metrics
Created by : Filip Neagoe
SNO | Required Data | Statistics
1 | No.of requirements | 6
2 | Average no. of written test cases per requirement | 11 / 6 ~ 2
3 | Total number of written test cases (for all the requirements) | 11
4 | Total number of executed test cases | 11
5 | No.of passed test cases | 6
6 | No.of failed test cases | 2
7 | No.of blocked test cases | 3
8 | No.of unexecuted test cases | 0
9 | Total number of identified defects | 5
10 | Critical defects count | 0
11 | Higher priority / severity defects count | 1
12 | Medium priority / severity defects count | 1
13 | Low priority /severity defects count | 3
14 | Customer defects | 0
15 | No.of defects found in UAT | 1 (during balance enquiry phase)

## RTM
Project Name | SNO | TC #ID | Status | Defect ID
Bank management application | 1 | TC_BANK_001 | PASSED | N/A
|  | TC_BANK_002 | PASSED | N/A
|  | TC_BANK_003 | PASSED | N/A
|  | TC_BANK_004 | PASSED | N/A
|  | TC_BANK_005 | PASSED | N/A
| 2 | TC_BANK_006 | PARTIAL PASSED | BANK_001
| 3 | TC_BANK_007 | PARTIAL PASSED | BANK_002
| 4 | TC_BANK_008 | PASSED | N/A
| 5 | TC_BANK_009 | FAILED | BANK_003
| 6 | TC_BANK_010 | FAILED | BANK_004
| 7 | TC_BANK_011 | PARTIAL PASSED | BANK_005

## Version_History
Project Name | Bank management application
Module | Guru99 project
Prepared by | Filip Neagoe
Version | v1.0 | Mentions: initial draft
| v2.0 | Mentions: few test cases need to be reviewed and updated + new functionalities implemented form scratch
Reviewed by | Product manager: Conal
Developers: Harry, Nick
QA team: Filip Neagoe
Approved by | Product manager: Jim

## Tasks
Dev tasks | QA tasks
Reviewing User stories | Reviewing User stories
Setting up Dev environment | Creating Test cases
Developing programs | Reviewing Test cases
Code review | Setting up Test environment
Creating Unit test cases | Creating Test data
Executing Unit tests | Executing Manual tests
Merging code | Automation Setup
Creating builds | Automation Design
Fixing bugs | Automating Test cases
Re-testing bugs
Regression testing
Demo user story